## Table 1
Student Affairs Program Review Schedule Updated July, 2024
Unit | Director/ Program Review Lead | Previous Reviews | Initial Meeting with AVP, & Dir. | Phase 1: Self- Study Begins 1 Month After Initial Meeting | Self Study Due to AVP, VP, and External Team 5-6 Months After Start | Phase 2: On-Site External Review Begins 1 Month After Self Study Due | External Review Draft Due to AVP & Director 1 Month After Review | Phase 3: Action Plan Due to AVP and VP 2 Months After External Review Report | Meet with AVP and VP within 1 Month | Brief Staff on Final Action Plan within 2 Weeks | 6 Month Action Plan Check with VP and AVP | AVP Area
Student Life | Jen Grossman-Leopard | UU 05, 12, 17, UU external 22 | Aug. 2024 | Sept. 2024 | March, 2025 | April, 2025 | May, 2025 | July, 2025 | Aug. 2025 | Aug. 2025 | Feb. 2026 | SL
Central Services (SAATS & SACM) | Jonathan Stewart, Carson Lonett | NA | Aug. 2024 | Sept. 2024 | March, 2025 | April, 2025 | May, 2025 | July, 2025 | Aug. 2025 | Aug. 2025 | Feb. 2026 | Central
SOGIE | Jordan 'JT' Todd | NA w/UHC | Aug. 2024 | Sept. 2024 | March, 2025 | April, 2025 | May, 2025 | July, 2025 | Aug. 2025 | Aug. 2025 | Feb. 2026 | A&B
Orientation | Casey Ouren | 00, 09, 14, 19 | Jan. 2025 | Feb. 2025 | July-Aug., 2025 | Aug-Sept. 2025 | Oct. 2025 | Dec. 2025 | Jan. 2026 | Jan. 2026 | July, 2026 | CELT
CMSS | TBD | 03, 08, 13, 20 | May, 2025 | June, 2025 | Nov., 2025 | Jan. 2026 | Feb. 2026 | April, 2026 | May, 2026 | May, 2026 | Nov. 2026 | A&B
Disability Services | Brittany Dioszeghy | 00, 09, 14, 21 | Jan. 2026 | Feb. 2026 | July-Aug., 2026 | Aug-Sept. 2026 | Oct. 2026 | Dec. 2026 | Jan. 2027 | Jan. 2027 | July, 2027 | A&B
Residence Life | Kathleen Campbell | 05, 09, 14, 22 | May, 2026 | June, 2026 | Nov., 2026 | Jan. 2027 | Feb. 2027 | April, 2027 | May, 2027 | May, 2027 | Nov. 2027 | SL
University Health Center | Kristina Blyer | 03, 10, 15, 22 | Jan. 2027 | Feb. 2027 | July- Aug., 2027 | Aug-Sept. 2027 | Oct. 2027 | Dec. 2027 | Jan. 2028 | Jan. 2028 | July, 2028 | HWB
Community Service-Learning | Kim Davidson | 06, 11, 16, 22 | May, 2027 | June, 2027 | Nov., 2027 | Jan. 2027 | Feb. 2028 | April, 2028 | May, 2028 | May, 2028 | Nov. 2028 | CELT
OSARP | Wendy Lushbaugh | 06, 11, 17, 22 | Aug. 2027 | Sept. 2027 | March, 2028 | April, 2028 | May, 2028 | July, 2028 | Aug., 2028 | Aug., 2028 | Feb. 2029 | SL
Health Promotion | Tia Mann | External 2023 | Jan. 2028 | Feb. 2028 | July- Aug., 2028 | Aug-Sept. 2028 | Oct. 2028 | Dec. 2028 | Jan. 2029 | Jan. 2029 | July, 2029 | HWB
University Career Center | Libby Westley | 02, 07, 12, 18, 23 | May, 2028 | June, 2028 | Nov., 2028 | Jan. 2029 | Feb. 2029 | April, 2029 | May, 2029 | May, 2029 | Nov. 2029 | CELT
Dean of Students | Hollie Hall | 23 | Aug. 2028 | Sept. 2028 | March, 2029 | April, 2029 | May, 2029 | July, 2029 | Aug., 2029 | Aug., 2029 | Feb. 2030 | DOS
University Recreation | Eric Nickel | 01, 07, 13, 18, 23 | Aug. 2028 | Sept. 2028 | March, 2029 | April, 2029 | May, 2029 | July, 2029 | Aug., 2029 | Aug., 2029 | Feb. 2030 | HWB
VALOR | TBD | New Dept. 2024 | Jan. 2029 | Feb. 2029 | July- Aug., 2029 | Aug-Sept. 2029 | Oct. 2029 | Dec. 2029 | Jan. 2030 | Jan. 2030 | July, 2030 | A&B
Counseling Center | David Onsetak | NA annual reporting | [9 empty] | HWB